## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
| Create an account | Authentication | Guest | New users can register an account by providing their name, email, and password to access the platform. | Hồng Nguyên | Done | iter1
| OTP screen | Authentication | Guest | Users enter a one-time code sent to their email to verify their identity during registration or password recovery. | Hồng Nguyên | Done | iter1
| Login/Logout | Authentication | Customer, Staff, Staff Manager | Users can log in using registered credentials and log out to end their session. | Hoàng Minh | Done | iter1
| Login with Google | Authentication | Customer, Staff, Staff Manager | Users can log in quickly using their existing Google account. | Quang Minh | Done | iter1
| Forgot password | Authentication | Customer, Staff, Staff Manager | Users can request a password reset by entering their registered email to receive a reset link or OTP. | Phong Quyền | Done | iter1
| Change password | Account | Customer, Staff, Staff Manager | Users can change their account password by verifying the current one and setting a new one. | Công Minh | Done | iter1
| View and Update Profile | Account | Customer, Staff, Staff Manager | Users can view and update personal information, contact details, address, and profile photo (avatar). | Quang Minh | Done | iter1
| View Homepage | General | Guest, Customer | Guests and customers can view the homepage to get an overview of the website services and features. | Hoàng Minh | Updated | iter1 | iter3
| View all motorcycles | General | Guest, Customer | Guests and customers can view a list of all available motorcycles, including photos, rental prices, and basic information. | Lê Quang Minh | Updated | iter1 | iter2
| View a motorcycle in detail | General | Guest, Customer | Guests and customers can view detailed information about a specific motorcycle, including images, specs, price, and included accessories. | Lê Quang Minh | Updated | iter1 | iter2
| View tourism location | Tourism Management | Guest, Customer | Guests and customers can browse suggested tourism destinations with photos, descriptions, and reference links. | Hồng Nguyên | Done | iter1 | None
| View FAQs | FAQ Management | Guest, Customer | Guests and customers can read frequently asked questions and their answers to better understand the service. | Phong Quyền | Done | iter1 | None
| View price list | Pricing Management | Guest, Customer | Guests and customers can view the current rental price list for all motorcycle types and rental durations. | Công Minh | Updated | iter1 | iter2
| View policies | Policy Management | Guest, Customer | Guests and customers can read the platform rental terms and conditions before making a reservation. | Hồng Nguyên | Done | iter1 | None
| Give contact | Contact Management | Guest, Customer | Users can submit a contact form to send questions or requests to the support team. | Hoàng Minh | Updated | iter1 | iter2
| View event/sales | Promotion Management | Guest, Customer | Guests and customers can view current promotions, discount events, and upcoming campaigns. | Lê Quang Minh | Done | iter1 | None
| Search motorcycles | Search & Recommendation | Guest, Customer | Guests and customers can search and filter motorcycles by brand, category, travel purpose, displacement, or price range. | Phong Quyền | Updated | iter1 | iter3
| Get motorcycle suggestions by demand | Search & Recommendation | Guest, Customer | Guests and customers can enter their travel needs such as touring, city riding, or fuel saving to receive suitable motorcycle suggestions from the system. | Công Minh | Done | iter1 | None
| Contact by chatbot | Chatbot | Guest, Customer | Guests and customers can chat with the system chatbot to get information and rental recommendations from the website. | Lê Quang Minh | Done | iter1 | None
| View booking history | Account | Customer | Customers can view a list of all past and current rental bookings and open any booking to see its full details. | Hoàng Minh | Updated | iter2 | iter3
| Choose pick up/return date/location | Rental Booking | Customer | Customers can select their preferred pickup and return dates and locations for the motorcycle rental. | Lê Quang Minh | Updated | iter2 | iter3
| Choose motorcycles | Rental Booking | Customer | Customers can browse and select an available motorcycle for their chosen rental period. | Phong Quyền | Updated | iter2 | iter3
| Choose accessories | Rental Booking | Customer | Customers can add optional accessories such as helmets or rain gear to their rental order. | Công Minh | Updated | iter2 | iter3
| Confirm personal information | Rental Booking | Customer | Customers can review and confirm their personal details before proceeding with the booking. | Hồng Nguyên | Updated | iter2 | iter3
| Confirm booking | Rental Booking | Customer | Customers can review the complete booking summary including motorcycle, accessories, dates, and total cost before finalizing. | Hoàng Minh | Updated | iter2 | iter3
| Make payment | Rental Booking | Customer | Customers can complete payment for their rental booking through available payment methods. | Lê Quang Minh | Updated | iter2 | iter3
| Apply voucher code | Rental Booking | Customer | Customers can enter a voucher or promo code at checkout to receive a discount on their rental. | Phong Quyền | Done | iter2 | None
| Cancel booking | Rental Booking | Customer | Customers can submit a cancellation request for an active booking and track the processing status. | Công Minh | Done | iter2 | None
| Extend booking | Rental Booking | Customer | Customers can request to extend their current rental period by selecting a new return date. | Hồng Nguyên | Done | iter2 | None
| Give rating and feedback | Rental Booking | Customer | Customers can rate the motorcycle and overall service quality after completing a rental. | Hoàng Minh | Done | iter2 | None
| Add to favorites | Favorite | Customer | Customers can save motorcycles they are interested in to a personal favorites list for easy access when planning a rental. | Hồng Nguyên | Done | iter2 | None
| Get motorcycle suggestions by tourism location | Tourism Management | Customer | Customers can select a tourism destination to receive motorcycle recommendations suitable for that route or terrain. | Phong Quyền | Done | iter2 | None
| View customer list | Customer Management | Staff | Staff can view, search, and access detailed profiles of all registered customers. | Công Minh | Done | iter2 | None
| Disable customer account | Customer Management | Staff | Staff can deactivate a customer account that has violated the platform rules. | Hồng Nguyên | Done | iter2 | None
| View overdue rentals | Customer Management | Staff | Staff can view a list of customers who have not returned their motorcycle by the agreed return date. | Hoàng Minh | Done | iter2 | None
| Provide customer consultation | Customer Management | Staff | Staff can provide consultation to customers regarding motorcycle options, rental pricing, accessories, policies, and active promotions. | Lê Quang Minh | Done | iter2 | None
| Confirm booking | Rental Management | Staff | Staff can review and approve pending booking requests submitted by customers. | Công Minh | Updated | iter2 | iter3
| Update booking status | Rental Management | Staff | Staff can update the booking status through each rental stage: confirmed → picked up → active → completed. | Hồng Nguyên | Updated | iter2 | iter3
| Cancel booking by staff | Rental Management | Staff | Staff can cancel a booking on behalf of the customer, including providing a reason and processing any applicable refund. | Hoàng Minh | Done | iter2 | None
| Handle extension request | Extension Management | Staff | Staff can view extension requests submitted by customers and approve or reject them after checking motorcycle availability. | Lê Quang Minh | Done | iter3 | None
| Handle cancellation request | Cancellation Management | Staff | Staff can view cancellation requests submitted by customers and approve or reject them. | Phong Quyền | Done | iter3 | None
| CRUD Motorcycle | Motorcycle Management | Staff | Staff can add, update, delete motorcycles and manage their availability status (available, rented, under maintenance, decommissioned). | Công Minh | Done | iter3 | None
| CRUD price list | Pricing Management | Staff | Staff can add new pricing entries, update existing rental rates, and remove outdated price records. | Hồng Nguyên | Done | iter3 | None
| CRUD FAQs | FAQ Management | Staff | Staff can add new FAQ entries, update existing questions and answers, and remove FAQs that are no longer relevant. | Hoàng Minh | Done | iter3 | None
| CRUD Tourism Location | Tourism Management | Staff | Staff can add new tourism destinations with photos and descriptions, update existing ones, and remove outdated entries. | Hồng Nguyên | Done | iter3 | None
| CRUD sales/events | Promotion Management | Staff | Staff can create new promotions or events with voucher codes, update active campaigns, and remove expired ones. | Phong Quyền | Done | iter3 | None
| CRUD accessories | Accessory Management | Staff | Staff can add new accessories, update stock and pricing information, and remove accessories that are no longer available. | Công Minh | Done | iter3 | None
| View customer feedback and contact requests | Feedback Management | Staff | Staff can view ratings and reviews from customers after completed rentals, and read contact form submissions sent by customers. | Hồng Nguyên | Done | iter3 | None
| Track rental motorcycle GPS location | Rental Management | Staff | Staff can view the real-time GPS location of motorcycles currently being rented on an interactive map. | Lê Quang Minh | Done | iter3 | None
| View staff list | Staff Management | Staff Manager | The manager can view, search, and access detailed profiles of all staff accounts along with their roles and permissions. | Hoàng Minh | Done | iter3 | None
| Disable staff account | Staff Management | Staff Manager | The manager can deactivate a staff account to revoke system access when needed. | Phong Quyền | Done | iter3 | None
| Manage staff roles and permissions | Staff Management | Staff Manager | The manager can assign or update roles and access permissions for staff members in the system. | Công Minh | Done | iter3 | None
| View dashboard | Dashboard & Analytics | Staff Manager | The manager can view a dashboard showing key metrics such as active rentals, revenue, motorcycle availability, and booking statistics. | Lê Quang Minh | Done | iter3 | None
| View rental analytics report | Dashboard & Analytics | Staff Manager | The manager can view reports on motorcycle rental performance, including most and least rented vehicles, demand trends, and discount recommendations. | Lê Quang Minh | Done | iter3 | None
Hoàng Minh
Effort Distribution
No | Full name | Student ID | Effort (%)
1 | Lê Quang Minh | DE190071 | 0%
2 | Lê Quang Minh | DE190071 | 0%
3 | Lê Quang Minh | DE190071 | 0%
4 | Lê Quang Minh | DE190071 | 0%
5 | Lê Quang Minh | DE190071 | 0%

## Iter1
Iteration Tracking - Iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Create an account | Authentication | New users can register an account by providing their name, email, and password to access the platform. | Hồng Nguyên | Done
| OTP screen | Authentication | Users enter a one-time code sent to their email to verify their identity during registration or password recovery. | Hồng Nguyên | Done
| Login/Logout | Authentication | Users can log in using registered credentials and log out to end their session. | Hoàng Minh | Done
| Login with Google | Authentication | Users can log in quickly using their existing Google account. | Quang Minh | Done
| Forgot password | Authentication | Users can request a password reset by entering their registered email to receive a reset link or OTP. | Phong Quyền | Done
| Change password | Account | Users can change their account password by verifying the current one and setting a new one. | Công Minh | Done
| View and Update Profile | Account | Users can view and update personal information, contact details, address, and profile photo (avatar). | Quang Minh | Done

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| View Homepage | General | Guests and customers can view the homepage to get an overview of the website services and features. | Hoàng Minh | Updated
| View all motorcycles | General | Guests and customers can view a list of all available motorcycles, including photos, rental prices, and basic information. | Lê Quang Minh | Updated
| View a motorcycle in detail | General | Guests and customers can view detailed information about a specific motorcycle, including images, specs, price, and included accessories. | Lê Quang Minh | Updated
| View tourism location | Tourism Management | Guests and customers can browse suggested tourism destinations with photos, descriptions, and reference links. | Hồng Nguyên | Done
| View FAQs | FAQ Management | Guests and customers can read frequently asked questions and their answers to better understand the service. | Phong Quyền | Done
| View price list | Pricing Management | Guests and customers can view the current rental price list for all motorcycle types and rental durations. | Công Minh | Updated
| View policies | Policy Management | Guests and customers can read the platform rental terms and conditions before making a reservation. | Hồng Nguyên | Done
| Give contact | Contact Management | Users can submit a contact form to send questions or requests to the support team. | Hoàng Minh | Updated
| View event/sales | Promotion Management | Guests and customers can view current promotions, discount events, and upcoming campaigns. | Lê Quang Minh | Done
| Search motorcycles | Search & Recommendation | Guests and customers can search and filter motorcycles by brand, category, travel purpose, displacement, or price range. | Phong Quyền | Updated
| Get motorcycle suggestions by demand | Search & Recommendation | Guests and customers can enter their travel needs such as touring, city riding, or fuel saving to receive suitable motorcycle suggestions from the system. | Công Minh | Done
| Contact by chatbot | Chatbot | Guests and customers can chat with the system chatbot to get information and rental recommendations from the website. | Lê Quang Minh | Done
| View booking history | Account | Customers can view a list of all past and current rental bookings and open any booking to see its full details. | Hoàng Minh | Updated
| Add to favorites | Favorite | Customers can save motorcycles they are interested in to a personal favorites list for easy access when planning a rental. | Hồng Nguyên | Done
| Choose pick up/return date/location | Rental Booking | Customers can select their preferred pickup and return dates and locations for the motorcycle rental. | Lê Quang Minh | Updated
| Choose motorcycles | Rental Booking | Customers can browse and select an available motorcycle for their chosen rental period. | Phong Quyền | Updated
| Choose accessories | Rental Booking | Customers can add optional accessories such as helmets or rain gear to their rental order. | Công Minh | Updated
| Confirm personal information | Rental Booking | Customers can review and confirm their personal details before proceeding with the booking. | Hồng Nguyên | Updated
| Confirm booking | Rental Booking | Customers can review the complete booking summary including motorcycle, accessories, dates, and total cost before finalizing. | Hoàng Minh | Updated
| Make payment | Rental Booking | Customers can complete payment for their rental booking through available payment methods. | Lê Quang Minh | Updated
| Apply voucher code | Rental Booking | Customers can enter a voucher or promo code at checkout to receive a discount on their rental. | Phong Quyền | Done
| Cancel booking | Rental Booking | Customers can submit a cancellation request for an active booking and track the processing status. | Công Minh | Done
| Extend booking | Rental Booking | Customers can request to extend their current rental period by selecting a new return date. | Hồng Nguyên | Done
| Give rating and feedback | Rental Booking | Customers can rate the motorcycle and overall service quality after completing a rental. | Hoàng Minh | Done
| Get motorcycle suggestions by tourism location | Tourism Management | Customers can select a tourism destination to receive motorcycle recommendations suitable for that route or terrain. | Phong Quyền | Done
| Manage booking list | Rental Management | Staff can view all rental bookings and open any booking to review its complete details. | Phong Quyền | Updated
| Confirm booking | Rental Management | Staff can review and approve pending booking requests submitted by customers. | Công Minh | Done
| Update booking status | Rental Management | Staff can update the booking status through each rental stage: confirmed → picked up → active → completed. | Hồng Nguyên | Done
| Cancel booking by staff | Rental Management | Staff can cancel a booking on behalf of the customer, including providing a reason and processing any applicable refund. | Hoàng Minh | Done
| Handle extension request | Extension Management | Staff can view extension requests submitted by customers and approve or reject them after checking motorcycle availability. | Lê Quang Minh | Done
| Handle cancellation request | Cancellation Management | Staff can view cancellation requests submitted by customers and approve or reject them. | Phong Quyền | Done

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| View customer list | Customer Management | Staff can view, search, and access detailed profiles of all registered customers. | Công Minh | Done
| Disable customer account | Customer Management | Staff can deactivate a customer account that has violated the platform rules. | Hồng Nguyên | Done
| View overdue rentals | Customer Management | Staff can view a list of customers who have not returned their motorcycle by the agreed return date. | Hoàng Minh | Done
| Provide customer consultation | Customer Management | Staff can provide consultation to customers regarding motorcycle options, rental pricing, accessories, policies, and active promotions. | Lê Quang Minh | Done
| Track rental motorcycle GPS location | Rental Management | Staff can view the real-time GPS location of motorcycles currently being rented on an interactive map. | Lê Quang Minh | Done
| CRUD Motorcycle | Motorcycle Management | Staff can add, update, delete motorcycles and manage availability status (available, rented, under maintenance, decommissioned). | Công Minh | Done
| CRUD price list | Pricing Management | Staff can add new pricing entries, update existing rental rates, and remove outdated price records. | Hồng Nguyên | Done
| CRUD FAQs | FAQ Management | Staff can add new FAQ entries, update existing questions and answers, and remove FAQs that are no longer relevant. | Hoàng Minh | Done
| CRUD Tourism Location | Tourism Management | Staff can add new tourism destinations with photos and descriptions, update existing ones, and remove outdated entries. | Hồng Nguyên | Done
| CRUD sales/events | Promotion Management | Staff can create new promotions or events with voucher codes, update active campaigns, and remove expired ones. | Phong Quyền | Done
| CRUD accessories | Accessory Management | Staff can add new accessories, update stock and pricing information, and remove accessories that are no longer available. | Công Minh | Done
| View customer feedback and contact requests | Feedback Management | Staff can view ratings and reviews from customers after completed rentals, and read contact form submissions sent by customers. | Hồng Nguyên | Done
| View staff list | Staff Management | The manager can view, search, and access detailed profiles of all staff accounts along with their roles and permissions. | Hoàng Minh | Done
| Disable staff account | Staff Management | The manager can deactivate a staff account to revoke system access when needed. | Phong Quyền | Done
| Manage staff roles and permissions | Staff Management | The manager can assign or update roles and access permissions for staff members in the system. | Công Minh | Done
| View dashboard | Dashboard & Analytics | The manager can view a dashboard showing key metrics such as active rentals, revenue, motorcycle availability, and booking statistics. | Lê Quang Minh | Done
| View rental analytics report | Dashboard & Analytics | The manager can view reports on motorcycle rental performance, including most and least rented vehicles, demand trends, and discount recommendations. | Lê Quang Minh | Done